## Sheet1
Sno | Desc | Status | Assignee | Testing Status | QA Owner | QA Comments | PR Status | Dev Comments | Category | Test Priority
SDT-4950 | Creating the QMS products | DONE | Mohd Waseemuddin | NA | Waseem | Already in prod, these product are in Deactivated state in production which must be removed if not used in SDT-6052
SDT-4991 | Connect Product Pricing | IN UAT | Mohd Waseemuddin |  | Waseem |  | Merged |  | QMS Pricing
SDT-5029 | Creation of price book entries | DONE | Mohd Waseemuddin | NA | Waseem | Already in prod, these PBE products are in Deactivated state in production which must be removed if not used in SDT-6052
SDT-5348 | Creating the Renewal Opportunity record types for QMS users | IN UAT | Mohd Waseemuddin | Failed | Waseem | I am not able to see the Renewal Record Type while creating the Opp as a QMS User | Merged | Nikhil - Renewals not needed now. | Renewal
SDT-5386 | CPQ quote line editor Investigation Story | IN UAT | Mohd Waseemuddin | Done | Waseem |  | Merged |  | Quotation
SDT-5388 | QMS closed lost reason updates for Prospects and Opps | IN UAT | Mohd Waseemuddin | Done | Waseem | Closed lost reasons available as per sheet additional one value on QMS opportunity record type Lost reason is "Lead time" which may need removing on Suspended_Closed_Reason__c | Merged |  | Lead Conversion
SDT-5389 | Ability to Create a QMS contract record | IN UAT | Mohd Waseemuddin | Done | Waseem |  | Merged |  | Contract
SDT-5421 | Creating a QMS quote template | IN UAT | Mohd Waseemuddin | Failed | Waseem | I am not able to see the new Quote Template | Merged |  | Quote Template
SDT-5831 | New field on the QMS Contract Object. | IN UAT | Mohd Waseemuddin | Done | Waseem | Post Deployment step to be done to assign QMS Contract Layout to QMS record Type contact | Merged | This QMS contract layout has 2 mandatory fields | Contract
Total Contract Value (duplicate label)
Payment Period
on layout only need to check if they are mandatory
SDT-5848 | Send the NSF along with Quote document for new sales | IN UAT | Mohd Waseemuddin |  | Waseem |  | Merged |  | Quote Template
SDT-5894 | QMS Contract fields display and validation rule updates | IN UAT | Mohd Waseemuddin | Done | Waseem |  | Merged |  | Contract
SDT-6103 | Fixing the issues with the subscription term | IN UAT | Mohd Waseemuddin |  | Waseem |  | Config - Merged |  | Subscription Term
SDT-6115 | Streamline contract creation process | IN UAT | Mohd Waseemuddin |  | Waseem |  | Merged |  | Contract
SDT-6123 | Create days fields on subscription fields | IN UAT | Mohd Waseemuddin | Done | Waseem | Have to assign QMS subscription layout to QMS users | Merged |  | Product Configuration | 4
SDT-6147 | Changes to the Quote Quick link fields | IN UAT | Mohd Waseemuddin | Done | Waseem |  | Merged
SDT-6463 | Adding in the New Service Forms and Checklish Docs | IN UAT | Mohd Waseemuddin |  | Waseem |  | Config - Merged |  | Template
SDT-7892 | Multi-site requirements | IN UAT | Mohd Waseemuddin |  | Waseem |  | Check for changes with owner |  | Multi-Site
SDT-8335 | "Apex CPU time limit exceeded" issue while products added in multiple groups(more than 2) | READY FOR LIVE | Mohd Waseemuddin | Failed | Waseem | Same Issue | Config - Merged |  | Bug